## Sheet1
Wornum Family Reunion Event Planning Guide
YR1 - January to December Year before the scheduled reunion
YR2 - January to July, Year of the reunion
| Tasks | Deadlines | Date Completed | Notes
Chapter
| Establish/Vote Leadership and Positions | Pre-reunion Kick off - October following reunion
| Establish meeting cadence (weekly, bi-weekly, monthly) | Pre-reunion Kick off - October following reunion
| Establish a Liason who will communicate information to the Wornum Connection Committee | Pre-reunion Kick off - October following reunion
| Create sub teams within the chapter to execute different tasks for reunion planning | Pre-reunion Kick off - October following reunion
Reunion Creative Direction
| Select a color for the reunion | YR 1 - January
| Select a slogan | YR 1 - January
Wornum Connection Committee
| Communicate Fundraiser timelines | Notify committee 8 weeks prior to each event
| Provide information for save the dates to go out - Reunion Date and Location | YR 1 - January
| Hotel booking link (that includes the discounted rates) | YR 1 - April
| Submit Welcome letter and Registration form to Wornum Connection Committee | YR 1 - July
Hotel
| Identify, research, and visit hotels | YR 1 - January (Start Date)
| Negotiate room prices and secure room blocks | YR 1 - March
| Negotiate food prices and meal options | YR 1 - March
| Secure a banquet room or space for the dinner | YR 1 - March
| Secure a hospitality suite/space for check-in | YR 1 - March
| Provide Wornum Connection Committee with hotel information and booking link | YR 1 - April
| Provide the hotel with the final meal order | YR 2 - Hotel will provide deadline
Banquet
| Put together a program of events for the evening | YR 1 - August
| Finalize décor plan and costs for the banquet space (if that service is not included) | YR 1 - August
| Secure a DJ and media equipment and costs | YR 1 - August
| Establish entertainment at the banquet | YR 1 - August
| Slideshow at banquet - final version completed | YR 2 - June
| Establish photographer (for bankquet/weekend) | YR 2 - January
Registration
| Establish registration fee for Children, Adults | YR 1 - May
| Compile a final list of attendees for check-in | YR 2 - July
| Set up a registration table/check-in area | Friday @ Reunion
Activities
| Identify and research activities for the weekend for Youth, Teens, Adults and Seniors | YR 1 - February (Start date)
| Finalize activities for the weekend for Youth, Teens, Adults and Seniors | YR 1 - July
| Secure needed spaces and items for all weekend activities | YR 1 - July
Information Guides
| Itenirary - Finalize the itinerary for the weekend and submit to Wornum Connection Committee | YR 1 - July
| Program - Finalize Design and layout the program/booklet | YR 2 - May
| Program - Proofread the booklet | YR 2 - May
| Program - Identify, research, and secure a vendor for printing | YR 2 - February (Start date)
| Program - Finalize and submit to Vendor for printing | YR 2 - May
| Resource Guide - Finalize a document of info/places of interest in the area and submit to Wornum Connection Committee | YR 2 - May
T-shirts
*Abide by the by-law (Logo over left chest). Design the back as desired
| Finalize the design | YR 1 - April
| Finalize the vendor | YR 1 - May
| Compile t-shirt count for the order | YR 2 - June (or after registration deadline)
| Submit t-shirt order | Deadline based on Vendor
Souvenir bags
| Select a bag (consider design and price) | YR 1 - April
| Finalize items that will be in the bag | YR 1 - April
| Create name tags/lanyards for each attendee | YR 2 - June
| Create and print out dinner/meal tickets | YR 2 - June
| Assemble bags for distribution | YR 2 - July